## Sheet1
AUN Project Mapping
No | Date | Project | Progress |  |  |  |  | Process Mapping | Deadline/Target | Note
|  |  | 20% | 40% | 60% | 80% | 100%
1 | 22/09/2022 | Swap Battery Station |  |  | 60% |  |  | 1. Search company swap battery in Indonesia 2. Looking for interview candidates (users Gogoro, Gesits & SWAP) 3. Survey Swap battery station 4. Decide Swap battery station 5. Propose & decided Swap Battery Company to Visit 6. Looking for & decided Eng-Ina Interpreter 7. Collecting data for company research (financial report for 3 years) | 21-23 November | No. 4 (PIC Swap Battery Station) No. 5 (SWAP Company Confirmation) No. 7 (Collecting Data) | 14.3%
2 | 26/09/2022 | Manufacturing Indonesia 2022 Support WingArc |  | 50% |  |  |  | 1. Submit Exhibitor Badges & Gold Visitor List 2. Submit Equipment Order 3. Order Other Equipment Outside Pamerindo 4. Received Exhibitor Badge 5. Exhibition |  | 5. Create Equipment list (A. TV + Standing + Kabel HDMI; B. 1 round table + 3 Kursi; C. 3 meja untuk laptop; D. 7 pcs kabel terminal dgn masing2 4 socket di dalamnya. *Kabel terminal cari 3 dulu) | 20%
3 | 26/09/2022 | Manufacturing Indonesia 2022 Support JETRO |  | 50% |  |  |  | 1. Order modem orbit 2. Looking for & Decided Interpreter (2) |  |  | 50%
4 |  | Manning Crew |  |  |  | 85% |  | 1. Prepare contact data manning crew agency 2. Propose Online Meeting to Manning Crew Agency 3. Online Meeting Manning Crew Agency - YMMC 4. Send & Received Questionaire |  | 1. Setting online meering : a. done : 10 b. no respond : 3 2. Collecting questionnaire from manning agency from total 9 meeting, already collected 7 | 25%